## Slide 1
COMPNINJA
Roadmap
Four tracks, twelve weeks, twelve milestones.
A roadmap of shipped features says nothing about whether the business is working. These four tracks each answer a different question, and only one of them is about code.
DEV
Development
three milestones
USE
Users
three milestones
REL
Relationships
three milestones
PRO
Profit
three milestones
Prepared 2026-08-19 · docs/ROADMAP.md stays the source of truth
Notes: Four tracks: Development, Users, Relationships, Profit. Three milestones each, one landing a week. This deck restates docs/ROADMAP.md as milestones on a calendar. When the two disagree, the repo file wins — move a line to its Shipped log the same commit it ships.

## Slide 2
WHY THIS PLAN AND NOT ANOTHER
The constraint is not the product.
COMPNINJA
2
0
outside users, at the last honest count (2026-08-06)
What is built
A Pro tier with billing, a private broker vault, 38 market pages, a comp corpus with retrieval, a lead inbox, a watchlist digest, share links with an ACL.
What is proven
The math, by test and by backtest. 1,520 tests gate every deploy. The reconciliation is scored against real corpus sales.
What is missing
A stranger. Nobody outside has run a report, uploaded a book, or paid. Every number above is a number about us.
THE ORDERING RULE FOR EVERYTHING THAT FOLLOWS
Work that moves a person from “never heard of it” to “ran a second report” outranks work that makes the report better. The product is not short of features; it is short of a first user. A thin result is a real answer — evidence to stop spending here, not a reason to spend more.
This is the roadmap's own position, not a new one: “as of 2026-08-06 the product had zero real outside users, so ‘can anyone find this’ is the binding constraint.” It is why Development is only one lane of four.
Notes: The zero is the whole argument for the ordering. If it stops being zero, re-order the deck around retention instead.

## Slide 3
FOUR TRACKS · TWELVE WEEKS · TWELVE MILESTONES
Only one of these four lanes is about code.
COMPNINJA
3
DEV
Development
What must exist before anything else on this page can be true.
D1 · Week 1
Outreach runs live for the first time
D2 · Week 3
Publishing refuses without a licence
D3 · Week 5
The digest sends on a schedule, not by hand
USE
Users
People who are not us, doing the thing without being asked.
U1 · Week 2
Ten reports run by people who are not us
U2 · Week 6
Somebody returns without being prompted
U3 · Week 10
Ten market buckets hold eight good comps
REL
Relationships
Brokers, advisers and counsel — the answers we cannot write ourselves.
R1 · Week 4
Three brokers hold a vault, handed over in person
R2 · Week 9
A broker publishes under their own credit name
R3 · Week 11
The attorney's three answers, in writing
PRO
Profit
Money that arrives from somebody who was free to keep it.
P1 · Week 7
The tier becomes buyable at all
P2 · Week 8
A stranger pays
P3 · Week 12
The broker network's revenue shape is decided
Read down a lane to see whether that half of the business is moving. A quarter where only DEV lands is a quarter that shipped a great deal and proved nothing.
Notes: Three milestones per track is a working default for twelve weeks. The tracks are deliberately unequal in effort — REL is mostly conversations, PRO is mostly a switch and a wait — because effort is not what they measure.

## Slide 4
DEV × 2 · USE × 1 · REL × 1
Weeks 1–4 · Getting in front of somebody
COMPNINJA
4
W01
Aug 17 – 23
DEV
Run the outreach that is already written
outreach.js runs real reports on real buildings and drafts a message each — built, never run live. Ten buildings, one market, --confirm. Same week: re-check Search Console — has the home page been crawled since Aug 8, and does it name itself as canonical yet?
D1 LANDS
W02
Aug 24 – 30
USE
Watch the ten, fix the worst drop
The visitor funnel now answers arrived → hit the wall → made an account → ran a report. Repair whichever gap is widest before adding anything. Nothing new ships this week that the funnel did not ask for.
U1 LANDS
W03
Aug 31 – Sep 06
DEV
Ship the licence gate before any broker has a vault
Decided 2026-08-12, not built: a licence field on the broker profile, and POST /api/vault/publish refuses without it. Verified means a named broker vouched; that must be enforced in code, not remembered. It has to land before R1, not after.
D2 LANDS
W04
Sep 07 – 13
REL
Hand three brokers a vault, in the room
VAULT_PASSKEY exists precisely so onboarding does not wait on the SQL editor. Read their real exports for lat/lng coverage — that measurement is what buys or kills import-time geocoding, deferred for want of a single real book.
R1 LANDS
WHAT THIS BLOCK IS JUDGED ON
Two lanes open at once on purpose: the licence gate (D2) is the one piece of code that must exist before a stranger holds a vault, so it lands the week before R1 does.

## Slide 5
DEV × 1 · USE × 1 · PRO × 2
Weeks 5–8 · Coming back, and paying
COMPNINJA
5
W05
Sep 14 – 20
DEV
Put the digest on a cadence
The one thing we send on our own initiative is manual-only by design. Drive the route from an external scheduler, weekly. Prove the high-water marks on a real send, and that unsubscribe survives a mail scanner fetching every link.
D3 LANDS
W06
Sep 21 – 27
USE
Make the second visit worth the trip
A saved property already reports what its market did while its owner was away, drawn from other people's searches. Land the digest on that, not on a generic desk. The return visit is the product; the first is the advert.
U2 LANDS
W07
Sep 28 – Oct 04
PRO
Unset PRO_AUDIENCE — that is the launch
Left set, the paid tier is live and unbuyable and the deployment looks perfectly healthy. Before flipping: one real card end to end, and confirm all nine Stripe events are ticked on the live endpoint — three of them sat inert for two weeks.
P1 LANDS
W08
Oct 05 – 11
PRO
Sell the $20 report where the lock is felt
The tile only appears on a report with locked comps, which is the only honest moment to ask. Measure lock seen → tile shown → checkout opened. Move the Stripe price before the copy, never after.
P2 LANDS
WHAT THIS BLOCK IS JUDGED ON
Retention is proved before the money is asked for. A first payment from somebody who was never going to return is a refund with a delay on it.

## Slide 6
REL × 2 · USE × 1 · PRO × 1
Weeks 9–12 · Credit, density, clearance
COMPNINJA
6
W09
Oct 12 – 18
REL
Close the credit loop for one broker
A broker publishes a comp under a credit name they stated themselves, and sees the citation count rise on it. That loop is the entire currency the broker tier trades in — brokers are paid in credit, not cash — and nobody outside has ever been through it.
R2 LANDS
W10
Oct 19 – 25
USE
Let real traffic thicken the corpus
Density is downstream of use, which is why it sits in this lane and not in DEV. Ten market/type buckets at eight good comps unblocks the browse page; the corpus_offer events on /admin are the gauge. Cross the backtest's 20-subject floor while watching.
U3 LANDS
W11
Oct 26 – Nov 01
REL
Get the attorney's three answers
Broker-data privacy — processing limits, deletion rights, liability for data a broker was not licensed to hold. It stopped being hypothetical the day private comps went into storage. It gates launch, not development, so it is asked now and built around.
R3 LANDS
W12
Nov 02 – 08
PRO
Decide what the broker network is worth
Hub ratings are the last v4 slice. Monetisation waits on the referral-fee answer from R3; if fees are barred, the fallback is lead visibility as a subscription benefit. Decide it in writing either way and move the line to the Shipped log.
P3 LANDS
WHAT THIS BLOCK IS JUDGED ON
No DEV milestone lands in the last block, and that is the test: if the quarter can only be finished by building something, the first eight weeks built the wrong thing.

## Slide 7
THE HONEST INVENTORY
Five things are built and switched off.
COMPNINJA
7
None of the first four milestones is blocked on code that does not exist. It is blocked on code nobody has turned on — which is a much cheaper problem, and a much easier one to leave unsolved for months.
outreach.js
Runs real reports on real buildings, publishes share links, drafts a message each. Bills nothing without --confirm.
NEVER RUN LIVE
PRO_AUDIENCE
Still set, so the paid tier is live and unbuyable. Unsetting it is the launch — there is no other switch.
STILL NARROWED
Watchlist digest
Route, copy rules and the /admin card all exist. A timer was refused on purpose; an external schedule was never added.
NO CADENCE
VAULT_PASSKEY
Shipped 2026-08-13 so a broker can be onboarded in the room instead of waiting on the SQL editor.
UNHANDED
Refund handlers
charge.refunded and the async-payment pair. Inert for two weeks; ticked on the live endpoint 2026-08-17.
NOW LIVE
Notes: This slide exists to stop the roadmap growing. Every item here was finished work that produced no outcome because a switch stayed off.

## Slide 8
GATED ON SOMEBODY ELSE
Three decisions this plan cannot make for itself.
COMPNINJA
8
For the attorney
Broker-data privacy: processing limits, deletion rights, and liability for data a broker was not licensed to hold.
Referral fees — whether they may be taken at all.
MLS re-share terms.
Gates launch, not development. Live since private comps entered storage.
For Chuck
The gut-check benchmark: which public figure a broker's book is judged against.
Pricing.
Day-one dashboard views.
Section 8 of the Ecosystem Plan. Shapes M5, does not block it.
For the owner
Which market gets the first outreach run, and whether it is one we already have corpus in.
Whether the licence gate binds us too — decided yes, 2026-08-12.
Whether any accuracy figure may be said publicly.
All three are answerable this month; none needs new data.
An unanswered question is not a blocked week — build around it and record the date it was asked.

## Slide 9
RUNNING UNDERNEATH THE FOUR LANES
The chores nobody has to approve.
COMPNINJA
9
ENGINEERING CHORES — PICK UP ANY OF THESE
A deploy checklist skill: tests → tailwind regen → pending migrations → push → verify live → devlog.
Extract tested pure modules out of server.js as they are touched — when touched, with tests first, never as a sweep.
Branch protection on main, once PR flow feels routine.
Market pages onto the rd-* tokens; regenerate og-image.png from the cut-card logo.
Re-measure PARALLEL_SEARCH on real traffic before ever flipping it on.
Fix marketOf() yielding “Canada” before a non-USD report is ever harvested.
PARKED — DECIDED, NOT FORGOTTEN
origin/ledger: Owen's in-repo ledger tooling. Parked 2026-08-04; its data files are already protected on main.
Per-type recommended lookbacks. Industrial moved to 24 months on measurement; the rest stay until measured the same way — priced sale comps per window, not total comps.
Explorer and seed pipeline stay pinned at 8 comps.
Plus-tier packaging ideas from the 2026-07-16 tiering draft.
Parked means a future reader should stop proposing it. Reviving one is a decision with a date, not a slow drift.

## Slide 10
WHAT BINDS EVERY SLIDE BEFORE THIS ONE
Principles
The product
A customer-first, daily-use tool growing toward Director-of-Asset-Management analysis. Favour client-side deterministic finance math — it costs nothing per run — and recurring-engagement loops over one-shot answers.
The brand
Calm UI. The brand is CompNinja, never Adler. A brand-identity change needs an explicit named yes, and so does any edit to visible copy.
The position
We are not a licensed broker. The site connects you with a local broker; it never is one. Every valuation is an automated estimate, never an appraisal — and that reaches the data, not only the copy.
The claim
Do not market “analyst-grade” before the comp audit scores 90%+. Nothing from the backtest ships to a marketing surface until it has crossed its own floor.
COMPNINJA
10

## Slide 11
HOW THIS DECK STAYS TRUE
A roadmap decays quietly.
COMPNINJA
11
These four habits are the whole defence. None of them is about writing more; three are about deleting on time.
01
Move the line the week it ships
A deck listing work already live is worse than no deck: it makes the reader distrust every other line. Move it to the Shipped log with its date, in the same commit.
02
Dates, never adverbs
“Recently”, “soon” and “currently” all age into lies. A date does not. Every claim on these slides carries the day it was last true.
03
Write the reason, not just the item
An entry saying only what to do gets re-argued next month. One saying why gets executed. Record what was rejected and what it would have cost — that is the most expensive thing here to regenerate.
04
The repo file wins
docs/ROADMAP.md is the source of truth and docs/ROADMAP-TEMPLATE.md is its shape. This deck is how the same plan is read out loud; when they disagree, the file is right.
Notes: If only one habit survives, make it the first. A stale roadmap is read as a lying one.